## Likelihood Guidance
Likelihood guidance
Likelihood represents the possibility that a given event will occur. Likelihood can be expressed using qualitative terms (frequent, likely, possible, unlikely, rare), as a percent probability, or as a frequency
Likelihood Rating | Title | Narrative | Frequency | Probability | Vulnerability | Event Timing
1 | Unlikely | Highly unlikely, but it may occur in exceptional circumstances. It could happen, but probably never will. | Over 5 years | <20% chance of occurrence over life of asset or project | High level of capabilities deployed and managed to address risks with redundant mechanisms in place that are regularly tested | Very slow onset, occurs over a year or more
2 | Possible | The event might occur at some time as there is a history of casual occurrence | 3-5 years | 21%-79% chance of occurrence over the life of the asset or project | Medium to high level of capabilities to address reisks with responses implemented and achieving objectives except under extreme conditions | Onset occurs in a matter of days to months
3 | Certain | The event is expected to occur in most circumstances as there is a history of regular occurrence | In the next year | 80% or greater chance of certain occurrence over life of asset or project | Little risk scenario planning performed, with low capabilities to address risk response. Some contingency plans in place | Rapid onset with little or no warning
Discussion questions during likelihood analysis
When was the last time risk associated with this area realized?
Are there any industry statistics available that offer objective data?
What past events and indicators can be used to forecast the future?
Are then any known threats, their capabilities, motivations?
What current vulnerabilities have been identified and how are they being handled?
Likelihood analysis
threat factors
skill
motive
opportunity
size
vulnerability
ease of exploit
awareness
intrustion detection

## Impact Guidance
Impact guidance
Impact (or consequence) refers to the extent to which a risk event might affect the enterprise.
Imact Rating | Title | Business Impact | [5 empty] | Technology & Security Impact
|  | Goals Achievement | Business Interruption | Financial | Reputational | Compliance | Safety | Confidentiality (privacy) | Integrity | Availability
1 | Minor | Some effect on business goals, but not material | Negligible. Critical functions and services unavailable for less than an hour | Little financial loss $$ to $$ | No reputational damage | Not reportable to regulators | No injuries to people | No breach to privacy | Little corruption to data that can be corrected quickly | Interruption of non critical services
2 | Moderate | Impact on goal attainment, but not widespread | Critical functions and services unavailable for one day causing stakeholder dissatisfaction | Moderate financial loss $$ to $$ | Short term reputational damage | Report of non compliance with immediate corrective action | Minimal injuries, nothing life threatening | Limited privacy breach with immediate corrective action | Slightly corrupt data that can interrupt operations | Interruption of primary services
3 | Extreme | Inability to meet multipe business goals | Critical functions and services unavailable for more than a day | Major financial impact Over $$ | Major media coverage | Significant failure to meet legal and regulatory requirements | Significant injuries | Widespread breach of privacy | Extensive or totally corrupt data that requires significant effort to correct | Extensive interruption of primary and secondary services
Discussion Questions |  | To what degree will this risk affect current business goals? | Are there any SLAs that define recovery time objectives? | Have we defined financial thresholds? | What levels of reputational damage should be considered? | Can this risk affect our compliance posture? | What are the safety implications of this risk? | Could PII be compromised? | Will this risk change or modify information? | Does this risk affect uptime of core services?

## Scenario Long List
Risk Scenario Category |  | Risk Scenario
1 | Portfolio establishment and maintenance | 1.1 | Wrong programs are selected for implementation and are misaligned with corporate strategy and priorities.
|  | 1.2 | There is duplication between initiatives.
2 | Program/projects life cycle management | 2.1 | Failing (due to cost, delays, scope creep, changed business priorities) projects are not terminated.
|  | 2.2 | Programs/projects fail due to not obtaining the active involvement throughout the program/project life cycle of all stakeholders (including sponsor).
3 | IT investment decision making | 3.1 | Business managers or representatives are not involved in important IT investment decision making (e.g., new applications, prioritization, new technology opportunities).
|  | 3.2 | The wrong software or infrastructure, in terms of cost, performance, features, compatibility, etc., is selected for implementation.
4 | IT expertise and skills | 4.1 | High IT staff turnover is impacting IT's ability to deliver core services
|  | 4.2 | There is an overreliance on key IT staff.
5 | Staff operations (human error and malicious intent) | 5.1 | Access rights from prior roles are abused.
|  | 5.2 | Information is input incorrectly by IT staff or system users.
|  | 5.3 | Hardware was tampered with intentionally (security devices, etc.).
6 | Information (data breach: damage, leakage and access) | 6.1 | Portable media containing sensitive data (CD, USB drives, portable disks, etc.) is lost/disclosed.
|  | 6.2 | Sensitive data is lost/disclosed through logical attacks.
|  | 6.3 | Sensitive information is accidentally disclosed due to failure to follow information handling guidelines.
7 | Architecture (architectural vision and design) | 7.1 | The enterprise architecture is complex and inflexible, obstructing further evolution and expansion leading to missed business opportunities.
|  | 7.2 | There is a failure to adopt and exploit new infrastructure or software in a timely manner.
8 | Infrastructure selection, implementation, operations (hardware, operating system) | 8.1 | The systems cannot handle transaction volumes when user volumes increase.
|  | 8.2 | Intermittently, there are failures of utilities (telecom, electricity).
|  | 8.3 | The IT in use is obsolete and cannot satisfy new business requirements (networking, security, database, storage, etc.).
|  | 8.4 | Hardware systems fail and lose availability.
9 | Software | 9.1 | The wrong software (cost, performance, features, compatibility, etc.) is selected for implementation or live.
|  | 9.2 | Intentional modification of software leading to wrong data or fraudulent actions.
|  | 9.3 | Unintentional modification of software leads to unexpected results.
|  | 9.4 | Application software is obsolete (e.g., old technology, poorly documented, expensive to maintain, difficult to extend, not integrated in current architecture).
10 | Business ownership of IT | 10.1 | Business does not assume accountability over those IT areas it should, e.g., functional requirements, development priorities, assessing opportunities through new technologies.
|  | 10.2 | Cost and ineffectiveness is related to IT related purchases outside of the procurement process.
|  | 10.3 | Inadequate requirements lead to ineffective service level agreements (SLAs).
11 | Supplier (selection/ performance, contractual compliance, termination of service and transfer) | 11.1 | Support and services delivered by vendors are inadequate and not in line with the SLA.
|  | 11.2 | There is non-compliance with software licence agreements (use and/or distribution of unlicenced software, etc.).
|  | 11.3 | There is an inability to transfer to alternative suppliers due to overreliance on current supplier.
|  | 11.4 | Cloud services are purchased by the business without the consultation/involvement of IT, resulting in inability to integrate the service with in-house services.
12 | Regulatory compliance | 12.1 | There is non-compliance with regulations, e.g., privacy, accounting.
13 | Malware | 13.1 | There is an intrusion of malware on critical operational servers.
|  | 13.2 | Regularly, there is infection of laptops with malware.
|  | 13.3 | Company data is stolen through unauthorized access gained by a phishing attack.
14 | Logical attacks | 14.1 | There is a service interruption due to denial-of-service attack.
|  | 14.2 | The web site is defaced.
|  | 14.3 | There is a virus attack.
15 | Acts of nature | 15.1 | There is an earthquake, major storm, flood, tornado
16 | Innovation | 16.1 | New and important technology trends are not identified or adopted in a timely manner.

## Scenario Long List Assessment
|  |  |  | Likelihood | Impact
Risk Scenario Category |  | Risk Scenario |  |  | Goals Achievement | Business Interruption | Financial | Reputational | Compliance | Safety | Confidentiality (privacy) | Integrity | Availability | Impact Average
1 | Portfolio establishment and maintenance | 1.1 | Wrong programs are selected for implementation and are misaligned with corporate strategy and priorities. | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333
|  | 1.2 | There is duplication between initiatives. | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333
2 | Program/projects life cycle management | 2.1 | Failing (due to cost, delays, scope creep, changed business priorities) projects are not terminated. | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.2222
|  | 2.2 | Programs/projects fail due to not obtaining the active involvement throughout the program/project life cycle of all stakeholders (including sponsor). | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333
3 | IT investment decision making | 3.1 | Business managers or representatives are not involved in important IT investment decision making (e.g., new applications, prioritization, new technology opportunities). | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333
|  | 3.2 | The wrong software or infrastructure, in terms of cost, performance, features, compatibility, etc., is selected for implementation. | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | IT expertise and skills | 4.1 | High IT staff turnover is impacting IT's ability to deliver core services | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5556
|  | 4.2 | There is an overreliance on key IT staff. | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1.6667
5 | Staff operations (human error and malicious intent) | 5.1 | Access rights from prior roles are abused. | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1.7778
|  | 5.2 | Information is input incorrectly by IT staff or system users. | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1.7778
|  | 5.3 | Hardware was tampered with intentionally (security devices, etc.). | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1.7778
6 | Information (data breach: damage, leakage and access) | 6.1 | Portable media containing sensitive data (CD, USB drives, portable disks, etc.) is lost/disclosed. | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 3 | 3 | 3 | 2.4444
|  | 6.2 | Sensitive data is lost/disclosed through logical attacks. | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2.5556
|  | 6.3 | Sensitive information is accidentally disclosed due to failure to follow information handling guidelines. | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 1.7778
7 | Architecture (architectural vision and design) | 7.1 | The enterprise architecture is complex and inflexible, obstructing further evolution and expansion leading to missed business opportunities. | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 3 | 2.5556
|  | 7.2 | There is a failure to adopt and exploit new infrastructure or software in a timely manner. | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1.4444
8 | Infrastructure selection, implementation, operations (hardware, operating system) | 8.1 | The systems cannot handle transaction volumes when user volumes increase. | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2
|  | 8.2 | Intermittently, there are failures of utilities (telecom, electricity). | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333
|  | 8.3 | The IT in use is obsolete and cannot satisfy new business requirements (networking, security, database, storage, etc.). | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 2.5556
|  | 8.4 | Hardware systems fail and lose availability. | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1.4444
9 | Software | 9.1 | The wrong software (cost, performance, features, compatibility, etc.) is selected for implementation or live. | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1111
|  | 9.2 | Intentional modification of software leading to wrong data or fraudulent actions. | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1.4444
|  | 9.3 | Unintentional modification of software leads to unexpected results. | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.4444
|  | 9.4 | Application software is obsolete (e.g., old technology, poorly documented, expensive to maintain, difficult to extend, not integrated in current architecture). | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | Business ownership of IT | 10.1 | Business does not assume accountability over those IT areas it should, e.g., functional requirements, development priorities, assessing opportunities through new technologies. | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1.5556
|  | 10.2 | Cost and ineffectiveness is related to IT related purchases outside of the procurement process. | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333
|  | 10.3 | Inadequate requirements lead to ineffective service level agreements (SLAs). | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 2.5556
11 | Supplier (selection/ performance, contractual compliance, termination of service and transfer) | 11.1 | Support and services delivered by vendors are inadequate and not in line with the SLA. | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.2222
|  | 11.2 | There is non-compliance with software licence agreements (use and/or distribution of unlicenced software, etc.). | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.2222
|  | 11.3 | There is an inability to transfer to alternative suppliers due to overreliance on current supplier. | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.2222
|  | 11.4 | Cloud services are purchased by the business without the consultation/involvement of IT, resulting in inability to integrate the service with in-house services. | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1.4444
12 | Regulatory compliance | 12.1 | There is non-compliance with regulations, e.g., privacy, accounting. | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.3333
13 | Malware | 13.1 | There is an intrusion of malware on critical operational servers. | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556
|  | 13.2 | Regularly, there is infection of laptops with malware. | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556
|  | 13.3 | Company data is stolen through unauthorized access gained by a phishing attack. | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556
14 | Logical attacks | 14.1 | There is a service interruption due to denial-of-service attack. | 2 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.4444
|  | 14.2 | The web site is defaced. | 1 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.4444
|  | 14.3 | There is a virus attack. | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556
15 | Acts of nature | 15.1 | There is an earthquake, major storm, flood, tornado | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333
16 | Innovation | 16.1 | New and important technology trends are not identified or adopted in a timely manner. | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333

## Scenario Long List Map
| Impact | 3 | 6.2, 8.3 | 7.1, 10.3, 13.1, 13.3, 14.3 | 13.2
|  | 2 | 5.2, 8.1, 14.2 | 5.1, 6.1, 6.3, 10.1, 11.1, 11.2, 12.1, 14.1 | 4.1, 4.2, 5.3, 9.3
8
|  | 1 | 2.1, 2.2, 7.2, 8.4, 10.2, 11.3 | 1.1, 1.2, 3.1, 3.2, 9.1, 9.2, 9.4, 16.1 | 8.2, 11.4, 15.1
9
10
|  |  | 1 | 2 | 3
Likelihood
11
12
13
14
15
16

## Scenario Ranking L+I (2)
|  | Likelihood | Impact | [9 empty] | Risk Rating | Risk Ranking
Risk Scenario |  |  | Goals Achievement | Business Interruption | Financial | Reputational | Compliance | Safety | Confidentiality (privacy) | Integrity | Availability | Impact
13.2 | Regularly, there is infection of laptops with malware. | 3 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556 | 5.5556
9.3 | Unintentional modification of software leads to unexpected results. | 3 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.4444 | 5.4444
5.3 | Hardware was tampered with intentionally (security devices, etc.). | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1.7778 | 4.7778
4.2 | There is an overreliance on key IT staff. | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1.6667 | 4.6667
10.3 | Inadequate requirements lead to ineffective service level agreements (SLAs). | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 2 | 2.5556 | 4.5556
13.1 | There is an intrusion of malware on critical operational servers. | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556 | 4.5556
13.3 | Company data is stolen through unauthorized access gained by a phishing attack. | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556 | 4.5556
14.3 | There is a virus attack. | 2 | 3 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.5556 | 4.5556
7.1 | The enterprise architecture is complex and inflexible, obstructing further evolution and expansion leading to missed business opportunities. | 2 | 3 | 3 | 3 | 2 | 3 | 1 | 2 | 3 | 3 | 2.5556 | 4.5556
4.1 | High IT staff turnover is impacting IT's ability to deliver core services | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5556 | 4.5556
14.1 | There is a service interruption due to denial-of-service attack. | 2 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.4444 | 4.4444
6.1 | Portable media containing sensitive data (CD, USB drives, portable disks, etc.) is lost/disclosed. | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 3 | 3 | 3 | 2.4444 | 4.4444
11.4 | Cloud services are purchased by the business without the consultation/involvement of IT, resulting in inability to integrate the service with in-house services. | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1.4444 | 4.4444
12.1 | There is non-compliance with regulations, e.g., privacy, accounting. | 2 | 2 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.3333 | 4.3333
15.1 | There is an earthquake, major storm, flood, tornado | 3 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 4.3333
8.2 | Intermittently, there are failures of utilities (telecom, electricity). | 3 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 4.3333
11.1 | Support and services delivered by vendors are inadequate and not in line with the SLA. | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.2222 | 4.2222
11.2 | There is non-compliance with software licence agreements (use and/or distribution of unlicenced software, etc.). | 2 | 2 | 1 | 2 | 3 | 3 | 1 | 3 | 3 | 2 | 2.2222 | 4.2222
5.1 | Access rights from prior roles are abused. | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1.7778 | 3.7778
6.3 | Sensitive information is accidentally disclosed due to failure to follow information handling guidelines. | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 1.7778 | 3.7778
6.2 | Sensitive data is lost/disclosed through logical attacks. | 1 | 3 | 2 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 2.5556 | 3.5556
8.3 | The IT in use is obsolete and cannot satisfy new business requirements (networking, security, database, storage, etc.). | 1 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 3 | 2 | 2.5556 | 3.5556
10.1 | Business does not assume accountability over those IT areas it should, e.g., functional requirements, development priorities, assessing opportunities through new technologies. | 2 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1.5556 | 3.5556
14.2 | The web site is defaced. | 1 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 2.4444 | 3.4444
9.2 | Intentional modification of software leading to wrong data or fraudulent actions. | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 2 | 1.4444 | 3.4444
1.1 | Wrong programs are selected for implementation and are misaligned with corporate strategy and priorities. | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3.3333
1.2 | There is duplication between initiatives. | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3.3333
16.1 | New and important technology trends are not identified or adopted in a timely manner. | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3.3333
3.1 | Business managers or representatives are not involved in important IT investment decision making (e.g., new applications, prioritization, new technology opportunities). | 2 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 3.3333
9.1 | The wrong software (cost, performance, features, compatibility, etc.) is selected for implementation or live. | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1111 | 3.1111
8.1 | The systems cannot handle transaction volumes when user volumes increase. | 1 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 2 | 3
3.2 | The wrong software or infrastructure, in terms of cost, performance, features, compatibility, etc., is selected for implementation. | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
9.4 | Application software is obsolete (e.g., old technology, poorly documented, expensive to maintain, difficult to extend, not integrated in current architecture). | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3
5.2 | Information is input incorrectly by IT staff or system users. | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1.7778 | 2.7778
7.2 | There is a failure to adopt and exploit new infrastructure or software in a timely manner. | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1.4444 | 2.4444
8.4 | Hardware systems fail and lose availability. | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1.4444 | 2.4444
10.2 | Cost and ineffectiveness is related to IT related purchases outside of the procurement process. | 1 | 1 | 1 | 3 | 1 | 2 | 1 | 1 | 1 | 1 | 1.3333 | 2.3333
2.2 | Programs/projects fail due to not obtaining the active involvement throughout the program/project life cycle of all stakeholders (including sponsor). | 1 | 2 | 1 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3333 | 2.3333
11.3 | There is an inability to transfer to alternative suppliers due to overreliance on current supplier. | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.2222 | 2.2222
2.1 | Failing (due to cost, delays, scope creep, changed business priorities) projects are not terminated. | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1.2222 | 2.2222